## Feuille1
	♨	♫	✏	Commentaire

API
Modeling	2
Versioning		2		loading still fuzzy, no versionning permissions

Annotations
manipulation / edition	2			Bugs positionement/selection
markdown syntax to javascript	2			Timecodes relatifs
the metadate 'is part of' -> some pages are part of several 'collections'.			1	Convention d'écriture RDFa: cest deja possible decrire dans labout du page

Tags, Indexation
adapting the indexing code to the new architecture			1
stabilizing filters and tags		2		améliorer le markdown pour la syntaxe des filtres
contextual tagging within a publication			1	no indexing; tags only for page

User permissions
authentication system	0,5
viewing/editing permissions	0,5			edits are not yet stockee
reverting/indexing permissions			0,5

Interface and layout tools
hotglue like interface	2			menu events
Miniature navigation map			0,5	APRES DEADLINE
grid and snapping helpers			0,5
CSS/templates setup	1
CSS/templates modifiable			1	How do we link to external stylesheets ?
annotation distribution actions: spring layout, cascade layout...			1	maybe spring not necessary

Media support
flash fallback for unsupported formats		1		apparantly mediaelement:js works with popcorn
youtube and vimeo support + synchronizing with annotations		2		through medielement.js or popcorn
setting in and out points for media (enabling basic sound and video editing)		2		through mediaquery fragment
once an annotation becomes active, play the video/sound contained inside		1		in global=events:js AA.listeningAnnotations
make it possible to link to (a specific time in) another video/sound		1		through mediaquery fragment
make slideshow in non-convoluted way		1		work behind is in the relative timecode, then the comportement should just be a bit different from normal annotation, but how to make this distinction on the level of interface?
Adjust appearance of sound player			1

Miscellaneous
migrating the old website			2
deployement			1

wrap up
better encoding and serving of media files			1
documentation			1
	10	12	12

	34.5